## Sheet1
Task Plan For Project
Backlog Item | List of product items | Task | Task owner | Time
Sprint 1 | Interface Prototype Design | Sales system user interface | Lizzy | 4/13-4/19
|  | Manage user interface prototypes | Richard
| ERD | ERD for project | Becky
Hilary
Sprint 2 | Database Design (manager) | Staff information | Hilary | 4/20-4/27
Income information
User information
Staff salary information
The ticket number information
| Database Design (user) | Item information | Lizzy | 4/20-4/27
Bus route information
Work schedule
The ticket price information
Sprint 3 | Sales system design | Login system | Richard | 4/20-4/27
Interface design
Create and connect database
Sprint 4 | Manager system | Create and connect database | Becky | 4/20-4/27
Dynamic database
Sprint 5 | Connect and change | Integrated databse and connect web | All memeber | 4/28-5/3
| Testing | Testing web | All memeber
Sprint 6 | Report | Finish Report | All memeber | 5/4-5/16